## Sheet1
Risk Decision Record
"If..." | "Then..." | Probability | Impact | Actions
Inactive member(s) | Unable to complete project on time | low | medium | Contingency actions with identified triggers
Persistent bugs | Unable to fix all bugs by deadline | low | low | Acceptable risk
Too many validation fields | Can't complete all validations by deadline | low | low | Acceptable risk
Device failure | Unable to complete project on time | low | medium | Preventive actions
Add more features | Unable to complete project on time | medium | low | Preventive actions
Incorrect work division | Unable to complete project on time | medium | low | Preventive actions
Sickness | Unable to contribute project on time | low | medium | Preventive actions
Unfamiliarity with tools | Unable to contribute effectively | medium | low | Acceptable risk
Burnout | Loss of motivation | medium | medium | Preventive actions
Tight schedule | Unable to complete project ontime | medium | medium | Preventive actions
Overlapping Projects | Unable to fully contribute to tasks | medium | medium | Preventive actions
Imbalanced workload | Unable to complete project ontime | medium | low | Acceptable risk
Loss of AI-assisted productivity | Reduced development efficiency | medium | medium | Preventive actions
Overwork | Stress | medium | medium | Preventive actions
Merge Conflicts | Difficult to merge branches | high | medium | Contingency actions with identified triggers
Opportunity Decision Record
If... | Then... | Probability | Impact | Actions
Successfully build the project | Create an online school management website | Medium | High | Exploit opportunity
Project delivered on time | Improve team reputation and credibility | High | High | Exploit opportunity
Website is user-friendly | Increase user adoption (students & teachers) | High | High | Enhance opportunity
System is stable and secure | Gain trust from school administrator | Medium | High | Enhance opportunity
Good UI/UX design implemented | Reduce training time for users | Medium | Medium | Enhance opportunity
Modular architecture used | Easier future maintenance & upgrades | Medium | Medium | Enhance opportunity
Project well documented | Future teams can extend the system easily | Medium | Medium | Share opportunity
Team collaboration is strong | Faster development and fewer errors | High | Medium | Enhance opportunity
Use modern tech stack | Better performance and scalability | Medium | High | Enhance opportunity
Successful demo/presentation | Attract more projects or funding | Low | High | Exploit opportunity